## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Mayank Bajaj | Week 1 | Duplicate security events found | Sprint 1 | Mayank Bajaj | Data Quality | Removed duplicates and validated dataset | Week 1 | Closed | Dataset validated
2 | Mayank Bajaj | Week 3 | Some features contained inconsistent values | Sprint 3 | Mayank Bajaj | Data/ML | Applied preprocessing and validation | Week 3 | Closed | Features standardized
3 | Mayank Bajaj | Week 4 | Prediction API returned incorrect field names | Sprint 4 | Mayank Bajaj | API | Standardized response schema | Week 4 | Closed | API response verified
4 | Mayank Bajaj | Week 4 | Dashboard could not display prediction response | Sprint 4 | Mayank Bajaj | Integration | Updated API mapping | Week 4 | Closed | Integration successful
5 | Mayank Bajaj | Week 5 | Risk score differed for test scenarios | Sprint 5 | Mayank Bajaj | Logic | Reviewed risk weights and formula | Week 5 | Closed | Risk calculation validated
6 | Mayank Bajaj | Week 6 | Related events were not grouped correctly | Sprint 6 | Mayank Bajaj | Logic | Updated correlation rules | Week 6 | Closed | Correlation validated
7 | Mayank Bajaj | Week 7 | Attack chain visualization had incorrect ordering | Sprint 7 | Mayank Bajaj | UI | Corrected event ordering | Week 7 | Closed | Visualization verified
8 | Mayank Bajaj | Week 8 | Minor UI alignment issue | Sprint 8 | Mayank Bajaj | UI | Updated responsive styling | Week 8 | Closed | UI verified